## 1. Exec Summary & Strategy
TRUSTRAIL INFRASTRUCTURE & VASP LICENSING ROADMAP
Complete Corporate, Regulatory, Technology & Banking Execution Plan across 3 Partners ¦ 16-Week Schedule
1. STRATEGIC ARCHITECTURE: THE 3 CORE UNITS
Unit Name | Scope & Responsibilities | Regulatory Anchor (Act 1154) | Target Deliverables | Lead Partner
UNIT 1: TrustRail-KYC | Identity Verification, Biometrics, Liveness, GhanaPost GPS, Document OCR, PII Masking & Pre-Flight CDD Validation | Act 1154 §33(1), AML Act 1044, Data Protection Act 843 | Standalone API (Port 3333), QoreID/Smile ID connectors, In-house CV engine, GhanaPost GPS, Mock/Live NIA client | Partner 1 (Tech Lead)
UNIT 2: TrustRail-AML | In-Flight Transaction Monitoring, Travel Rule Payloads, On-Chain Forensics, goAML STR/CTR Reports, Batch Re-Screening | Act 1154 §33(3)-(4), BoG Enhanced MM Tiers, FIC Directives | OpenSanctions engine, Travel Rule payload engine, Chainalysis/TRM integration, 24h STR alert pipeline, Re-screening worker | Partner 2 (Compliance Lead)
UNIT 3: TrustRail-Rail | CediRamp On/Off-Ramp, Mobile Money Rails (MTN MoMo/Telecel), Base L2 USDC Settlement, Segregated Custody Float | Act 1154 Schedule Category 4 (Payment Processor) & Category 1 (Dealing) | Production MoMo API, Multi-sig custodial float, Idempotent quote/order engine, Signed webhooks, Bank float partnership | Partner 3 (Ops & Banking Lead)
2. PARTNER RESPONSIBILITY & GOVERNANCE MATRIX
Partner | Primary Executive Role | Core Workstream Ownership | External Institutional Counterparts | Time Commitment
PARTNER 1 | Chief Technology Officer / Tech Lead | Unit 1 Core (KYC & Biometrics), Unit 3 Backend Architecture, API Gateway, Security Hardening, Cryptographic Webhooks & L2 Settlement | Technical Vendor Dev Relations (Smile ID, QoreID, Infura/Base, Cloudflare, External Pentest Auditors) | Full-Time (40h/wk)
PARTNER 2 | Chief Compliance Officer / RegTech Lead | Unit 2 Core (AML & Travel Rule), OpenSanctions, FIC goAML Reporting, AML/CFT Policies, Data Protection (DPC) & Cybersecurity Authority (CSA) filings | Financial Intelligence Centre (FIC), Data Protection Commission (DPC), Forensics (Chainalysis/TRM Labs), Legal Counsel | Full-Time (40h/wk)
PARTNER 3 | Chief Operating Officer / Banking & Reg Lead | Office of Registrar of Companies (ORC), Bank of Ghana (VARO/VAD) Sandbox Application, Partner Bank Escrow/Float Structuring, MTN MoMo Contract | Office of Registrar of Companies, Bank of Ghana (VARO), Partner Banks (Stanbic/Ecobank/CalBank), MTN Ghana, B2B Clients | Full-Time (40h/wk)
3. KEY PROGRAM MILESTONES & REGULATORY GATES
Milestone Gate | Target Window | Required Deliverables & Pre-conditions | Exit Gate / Success Verification | Status
M1: Corporate Formation & Standalone KYC | Week 4 | ORC Incorporation, TIN/GRA, SSNIT, TrustRail-KYC completed with QoreID, Smile ID & GhanaPost GPS | Certificate of Incorporation issued, 100% KYC test pass, verified live QoreID check | COMPLETED
M2: AML Travel Rule & Partner Bank Float | Week 8 | Travel Rule payload engine, goAML STR pipeline, DPC Controller Cert, Bank escrow terms agreed | Mock Travel Rule message verified, DPC certificate issued, Partner Bank term sheet signed | IN PROGRESS
M3: Bank of Ghana VARO Sandbox Filing | Week 12 | Complete 9-part VASP statutory application submitted to Bank of Ghana VARO under Act 1154 | Official acknowledgment, receipt of application fee, and VARO interview scheduled | PLANNED
M4: Live Sandbox Operations & B2B Launch | Week 16 | Production MTN MoMo live, Base mainnet settlement, live B2B partner pilot (Mmabia & 1 other) | Live GHS 500k volume processed in sandbox with zero AML/KYC audit infractions | PLANNED

## 2. Master Schedule (WBS)
TRUSTRAIL 16-WEEK MASTER WORK BREAKDOWN SCHEDULE
Complete Inventory Across Corporate Setup, Licensing, Technology, AML, Banking & Operations
Task ID | Workstream | Task Name & Description | Lead Partner | Start Wk | End Wk | Duration | Status | Deliverable | Regulatory Anchor
CORP-01 | Corporate & Legal | Company Incorporation (ORC) - Ltd by Shares | Partner 3 | W1 | W2 | 2 wks | DONE | Certificate of Incorporation & Constitution | Companies Act 2019 (Act 992)
CORP-02 | Corporate & Legal | GRA Taxpayer Identification (TIN) & VAT Setup | Partner 3 | W2 | W3 | 2 wks | DONE | Corporate TIN & Tax Clearance Portal | GRA Revenue Administration Act
CORP-03 | Corporate & Legal | SSNIT Employer Registration & Certificate | Partner 3 | W2 | W3 | 2 wks | DONE | SSNIT Employer Certificate | National Pensions Act 766
CORP-04 | Corporate & Legal | Physical Office Lease & Business Operating Permit | Partner 3 | W2 | W4 | 3 wks | DONE | Commercial Lease & MMDA Operating Permit | Act 1154 §21 (Registered Office)
CORP-05 | Corporate & Legal | Board Resolution & 3-Director Governance Setup | All Partners | W2 | W3 | 2 wks | DONE | Board Minutes, Independent Director Appt | Act 1154 §23 (Min 3 Directors)
CORP-06 | Corporate & Legal | Shareholders' Agreement & IP Assignment | All Partners | W3 | W5 | 3 wks | IN PROGRESS | Executed SHA & Technology Transfer Agreement | Act 1154 §42 (Shareholding Rules)
CORP-07 | Corporate & Legal | Appointment of ICAG Statutory External Auditor | Partner 3 / 2 | W4 | W6 | 3 wks | IN PROGRESS | Auditor Engagement Letter (ICAG Member) | Act 1154 §30-31 (Auditor Duty)
CORP-08 | Corporate & Legal | Corporate Banking Account Setup (Operational) | Partner 3 | W3 | W5 | 3 wks | IN PROGRESS | Stanbic/Ecobank GHS & USD Operating Accounts | Corporate Banking
KYC-101 | Unit 1 (KYC) | Ghana Card Validation & DOB Rules | Partner 1 | W1 | W2 | 2 wks | DONE | validation.ts (regex + age >= 18 check) | Act 1154 §33(1), Act 1044
KYC-102 | Unit 1 (KYC) | QoreID & Smile ID Multi-Vendor Client | Partner 1 | W1 | W3 | 3 wks | DONE | IdVerificationClient (QoreID + Smile ID) | Act 1154 §33(1)
KYC-103 | Unit 1 (KYC) | In-House CV Biometrics & OCR Engine | Partner 1 | W2 | W4 | 3 wks | DONE | src/inhouse/ (face match, OCR, cert) | Act 1154 §33(1)
KYC-104 | Unit 1 (KYC) | GhanaPost GPS Proof of Address Validator | Partner 1 | W2 | W3 | 2 wks | DONE | src/address/ghanapost.ts | BoG Tier 2/3 Guidelines
KYC-105 | Unit 1 (KYC) | PII Masking & Privacy Guard | Partner 1 | W3 | W4 | 2 wks | DONE | src/utils/masking.ts | Data Protection Act 843 §27
KYC-106 | Unit 1 (KYC) | Standalone Web Server & Diagnostic CLI | Partner 1 | W3 | W4 | 2 wks | DONE | src/server.ts (Port 3333), diagnostics.ts | Internal Readiness
KYC-107 | Unit 1 (KYC) | CediRamp Drop-In Integration Adapter | Partner 1 | W4 | W5 | 2 wks | DONE | src/adapter/cediramp.ts | CediRamp Integration
KYC-108 | Unit 1 (KYC) | NIA Direct Enterprise Data Sharing Integration | Partner 1 / 3 | W9 | W12 | 4 wks | PLANNED | Live NiaClient (post-contract) | National Identity Register
AML-201 | Unit 2 (AML) | OpenSanctions Screening Client | Partner 2 | W3 | W4 | 2 wks | DONE | OpenSanctionsClient (fuzzy /match API) | Act 1154 §33(1), UN/OFAC
AML-202 | Unit 2 (AML) | Sanction vs PEP/Adverse Media Classification | Partner 2 | W3 | W4 | 2 wks | DONE | Hard block vs EDD review flags | Act 1044 EDD Rules
AML-203 | Unit 2 (AML) | Periodic Batch Re-Screening Worker | Partner 2 | W4 | W5 | 2 wks | DONE | src/workers/rescreening.ts | Ongoing Monitoring
AML-204 | Unit 2 (AML) | Travel Rule Originator/Beneficiary Engine | Partner 2 / 1 | W5 | W8 | 4 wks | IN PROGRESS | Travel Rule JSON-LD message generator | Act 1154 §33(3)-(4)
AML-205 | Unit 2 (AML) | Travel Rule Network Gateway (Notabene/IVMS) | Partner 2 | W7 | W10 | 4 wks | PLANNED | VASPPromise / IVMS101 protocol bridge | FATF Recommendation 16
AML-206 | Unit 2 (AML) | On-Chain Forensic Wallet Screening | Partner 2 / 1 | W6 | W9 | 4 wks | IN PROGRESS | Chainalysis / TRM Labs API adapter | Act 1154 §33(1)
AML-207 | Unit 2 (AML) | FIC goAML STR / CTR 24h Reporting Pipeline | Partner 2 | W8 | W11 | 4 wks | PLANNED | Automated STR XML generator for goAML | Act 1044 §30, Act 1154 §33
AML-208 | Unit 2 (AML) | BoG Transaction Threshold & Velocity Enforcement | Partner 2 / 1 | W4 | W6 | 3 wks | DONE | GHS 25k limits & velocity alerts | BoG Mobile Money Guidelines
RAIL-301 | Unit 3 (Rail) | CediRamp Quoting & Order Engine (Base L2) | Partner 1 | W1 | W4 | 4 wks | DONE | Base Sepolia on/off-ramp quotes & orders | Act 1154 Category 4
RAIL-302 | Unit 3 (Rail) | Idempotent Webhooks & Replay Protection | Partner 1 | W3 | W4 | 2 wks | DONE | HMAC-SHA256 webhooks & Idempotency-Key | Security Best Practices
RAIL-303 | Unit 3 (Rail) | Multi-Sig & HSM/MPC Custody Float Setup | Partner 1 / 3 | W7 | W10 | 4 wks | IN PROGRESS | Safe / Fireblocks multi-sig float wallet | Act 1154 §40 (Custody)
RAIL-304 | Unit 3 (Rail) | MTN MoMo Direct Enterprise Production Rail | Partner 3 / 1 | W8 | W12 | 5 wks | PLANNED | Live MTN Open API direct billing bridge | Payment Systems Act 987
RAIL-305 | Unit 3 (Rail) | Partner Bank Escrow & Ring-Fenced Float Account | Partner 3 | W6 | W10 | 5 wks | IN PROGRESS | Bank escrow trust agreement for Cedi float | Act 1154 §32 (Solvency)
RAIL-306 | Unit 3 (Rail) | Base Mainnet Deployment & Liquidity Seeding | Partner 1 / 3 | W11 | W14 | 4 wks | PLANNED | Live contract deployment on Base Mainnet | Production Launch
RAIL-307 | Unit 3 (Rail) | Automated Liquidity Rebalancing & Hedging | Partner 1 | W12 | W15 | 4 wks | PLANNED | Cedi/USDC float rebalancing daemon | Treasury Ops
REG-401 | Regulatory & BoG | Data Protection Commission (DPC) Registration | Partner 2 | W3 | W6 | 4 wks | IN PROGRESS | DPC Data Controller Certificate | Data Protection Act 843
REG-402 | Regulatory & BoG | Designation of MLRO & FIC goAML Portal Reg | Partner 2 | W4 | W7 | 4 wks | IN PROGRESS | FIC goAML Account & MLRO Appointment | Act 1044 §30, Act 1154 §33
REG-403 | Regulatory & BoG | Cybersecurity Authority (CSA) CII Registration | Partner 1 / 2 | W7 | W10 | 4 wks | PLANNED | CSA Cybersecurity Accreditation | Cybersecurity Act 1038, Act 1154 §36
REG-404 | Regulatory & BoG | Board AML/CFT, CDD & Whistleblower Policies | Partner 2 | W5 | W8 | 4 wks | IN PROGRESS | Board-Approved AML/CFT Compliance Manual | Act 1154 §33-34
REG-405 | Regulatory & BoG | Fit-and-Proper Dossiers for All 3 Partners | All Partners | W6 | W9 | 4 wks | IN PROGRESS | Police Clearance, Net Worth, Credit Checks | Act 1154 §24-25 (Fit & Proper)
REG-406 | Regulatory & BoG | Bank of Ghana VARO Sandbox Application Dossier | Partner 3 / 2 | W8 | W12 | 5 wks | IN PROGRESS | Complete 9-Part VASP Application Binder | Act 1154 §43-50 (Sandbox)
REG-407 | Regulatory & BoG | Independent Cybersecurity Pentest & Audit | Partner 1 / 3 | W10 | W13 | 4 wks | PLANNED | Third-Party Pentest Attestation Report | Act 1154 §36 (Cybersecurity)
REG-408 | Regulatory & BoG | Professional Indemnity & Custody Insurance | Partner 3 | W9 | W12 | 4 wks | PLANNED | Cyber/Crime Insurance Policy Cover | Act 1154 §32 (Insurance)
REG-409 | Regulatory & BoG | NIA Enterprise Contract & NIR Access Grant | Partner 3 | W8 | W11 | 4 wks | PLANNED | Executed NIA Data Access Agreement | NIR Identity Verification
REG-410 | Regulatory & BoG | BoG Sandbox Supervisory Demo & Defense | All Partners | W13 | W15 | 3 wks | PLANNED | Interactive VARO Technical Walkthrough | Act 1154 §45 (Sandbox Grant)

## 3. 16-Week Gantt Timeline
TRUSTRAIL 16-WEEK GANTT TIMELINE VISUALIZER
Blue = Partner 1 (Tech) ¦ Green = Partner 2 (Compliance) ¦ Orange = Partner 3 (Ops/Banking) ¦ Purple = All Partners
Task ID | Task Description | Lead | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
CORP-01 | Company Incorporation (ORC) - Ltd by Shares | Partner 3
CORP-02 | GRA Taxpayer Identification (TIN) & VAT Setup | Partner 3
CORP-03 | SSNIT Employer Registration & Certificate | Partner 3
CORP-04 | Physical Office Lease & Business Operating Permit | Partner 3
CORP-05 | Board Resolution & 3-Director Governance Setup | All Partners
CORP-06 | Shareholders' Agreement & IP Assignment | All Partners
CORP-07 | Appointment of ICAG Statutory External Auditor | Partner 3 / 2
CORP-08 | Corporate Banking Account Setup (Operational) | Partner 3
KYC-101 | Ghana Card Validation & DOB Rules | Partner 1
KYC-102 | QoreID & Smile ID Multi-Vendor Client | Partner 1
KYC-103 | In-House CV Biometrics & OCR Engine | Partner 1
KYC-104 | GhanaPost GPS Proof of Address Validator | Partner 1
KYC-105 | PII Masking & Privacy Guard | Partner 1
KYC-106 | Standalone Web Server & Diagnostic CLI | Partner 1
KYC-107 | CediRamp Drop-In Integration Adapter | Partner 1
KYC-108 | NIA Direct Enterprise Data Sharing Integration | Partner 1 / 3
AML-201 | OpenSanctions Screening Client | Partner 2
AML-202 | Sanction vs PEP/Adverse Media Classification | Partner 2
AML-203 | Periodic Batch Re-Screening Worker | Partner 2
AML-204 | Travel Rule Originator/Beneficiary Engine | Partner 2 / 1
AML-205 | Travel Rule Network Gateway (Notabene/IVMS) | Partner 2
AML-206 | On-Chain Forensic Wallet Screening | Partner 2 / 1
AML-207 | FIC goAML STR / CTR 24h Reporting Pipeline | Partner 2
AML-208 | BoG Transaction Threshold & Velocity Enforcement | Partner 2 / 1
RAIL-301 | CediRamp Quoting & Order Engine (Base L2) | Partner 1
RAIL-302 | Idempotent Webhooks & Replay Protection | Partner 1
RAIL-303 | Multi-Sig & HSM/MPC Custody Float Setup | Partner 1 / 3
RAIL-304 | MTN MoMo Direct Enterprise Production Rail | Partner 3 / 1
RAIL-305 | Partner Bank Escrow & Ring-Fenced Float Account | Partner 3
RAIL-306 | Base Mainnet Deployment & Liquidity Seeding | Partner 1 / 3
RAIL-307 | Automated Liquidity Rebalancing & Hedging | Partner 1
REG-401 | Data Protection Commission (DPC) Registration | Partner 2
REG-402 | Designation of MLRO & FIC goAML Portal Reg | Partner 2
REG-403 | Cybersecurity Authority (CSA) CII Registration | Partner 1 / 2
REG-404 | Board AML/CFT, CDD & Whistleblower Policies | Partner 2
REG-405 | Fit-and-Proper Dossiers for All 3 Partners | All Partners
REG-406 | Bank of Ghana VARO Sandbox Application Dossier | Partner 3 / 2
REG-407 | Independent Cybersecurity Pentest & Audit | Partner 1 / 3
REG-408 | Professional Indemnity & Custody Insurance | Partner 3
REG-409 | NIA Enterprise Contract & NIR Access Grant | Partner 3
REG-410 | BoG Sandbox Supervisory Demo & Defense | All Partners
MILESTONE GATE CHECKPOINTS
Week 4 | M1: Corporate Formation & Standalone KYC | COMPLETED |  |  |  | ★
Week 8 | M2: AML Travel Rule & Partner Bank Float | IN PROGRESS | [7 empty] | ★
Week 12 | M3: Bank of Ghana VARO Sandbox Filing | PLANNED | [11 empty] | ★
Week 16 | M4: Live Sandbox Operations & B2B Launch | PLANNED | [15 empty] | ★

## 4. Partner RACI & Governance
PARTNER RACI MATRIX & GOVERNANCE ALLOCATION
R = Responsible (Executes) ¦ A = Accountable (Approves) ¦ C = Consulted ¦ I = Informed
Operational / Regulatory Domain | Partner 1 (Tech) | Partner 2 (Compliance) | Partner 3 (Ops/Banking) | Key Governance Notes
Company Incorporation (ORC) & Board Setup | C | C | R / A | P3 executes Registrar of Companies filings & lease
Shareholders' Agreement (SHA) & Equity Vesting | R / A | R / A | R / A | Unanimous approval required across all 3 partners
TrustRail-KYC Engine & Architecture | R / A | C | I | P1 leads codebase; P2 verifies Act 1044 alignment
Biometric & Document OCR Integrity | R / A | C | I | P1 maintains algorithm benchmarks; P2 audits accuracy
OpenSanctions & Watchlist Configuration | C | R / A | I | P2 sets fuzzy match threshold; P1 maintains worker uptime
Travel Rule Protocol & Integration | R | R / A | C | P2 defines IVMS101 schema; P1 connects network SDK
goAML & FIC Suspicious Reporting | C | R / A | C | P2 acts as designated MLRO / AML Officer with FIC
Bank of Ghana VARO Sandbox Engagement | C | C | R / A | P3 manages primary regulatory liaison with BoG officials
Partner Bank Escrow & Float Structuring | C | C | R / A | P3 executes trust agreements with banking partners
MTN MoMo Enterprise Direct Agreement | C | C | R / A | P3 drives telco negotiations; P1 integrates APIs
Data Protection (Act 843) Audit & Filing | C | R / A | I | P2 manages Data Protection Commission registration
Cybersecurity (CSA) & Pentest Audit | R / A | C | C | P1 coordinates third-party security auditors
B2B Fintech & Crypto Client Onboarding | C | C | R / A | P3 leads sales; P1 & P2 provide tech/compliance support
ESTIMATED WEEKLY TIME ALLOCATION (HOURS / WEEK)
Phase / Execution Window | Partner 1 (Tech) | Partner 2 (Compliance) | Partner 3 (Ops/Banking) | Combined Team Effort
Phase 1: Weeks 1 - 4 (Corporate & KYC Build) | 40 | 30 | 35 | 0
Phase 2: Weeks 5 - 8 (AML, Travel Rule & Bank Escrow) | 35 | 40 | 35 | 0
Phase 3: Weeks 9 - 12 (BoG Filing & Rail Hardening) | 35 | 35 | 40 | 0
Phase 4: Weeks 13 - 16 (Live Sandbox & Launch) | 40 | 35 | 40 | 0

## 5. Complete Budget & Costs
TRUSTRAIL PROGRAM BUDGET & COST ESTIMATES
Includes Corporate Registration, Regulatory Licensing, Technology Stack, Legal & Audits (FX @ 15.5 GHS/USD)
Category | Item / Provider | Operational Purpose | Pricing Structure | Setup / Filing ($) | Monthly Cost ($) | Monthly Cost (GHS)
Corporate Formation | ORC Registration & Stamp Duty | Company Incorporation & Stated Capital | One-Time Statutory Filing | 450 | 0 | 0
Corporate Formation | Physical Office & Operating Permit | Accra Office Lease & MMDA Permit | Annual Lease + Permit | 2500 | 300 | 0
Corporate Legal | External Legal Counsel | SHA, Governance & Regulatory Advice | Fixed Legal Retainer | 1500 | 250 | 0
Statutory Audit | ICAG External Audit Firm | Statutory Annual Financial & AML Audit | Annual Engagement Fee | 2000 | 0 | 0
Regulatory Filing | Bank of Ghana (VARO) | VASP Sandbox Application Fee | Official Regulatory Filing | 2500 | 0 | 0
Data Protection | Data Protection Commission (DPC) | Data Controller Certification (Act 843) | Annual Registration | 350 | 0 | 0
Cybersecurity | Cybersecurity Authority (CSA) | CII Registration & CSP Accreditation | Annual Regulatory Fee | 500 | 0 | 0
Insurance | Underwriters / Broker | Cyber Liability & Custody Insurance | Annual Insurance Policy | 2000 | 150 | 0
Identity Verification | QoreID | Ghana Card Registry Verification | Per Lookup (~$0.15/check) | 0 | 150 | 0
Identity Verification | Smile ID | Biometric 1:1 Face Match & Liveness | Per Job (~$0.25/check) | 500 | 250 | 0
Identity Verification | NIA Direct Enterprise | National Identity Register Official API | Annual Enterprise Contract | 1000 | 300 | 0
AML & Watchlists | OpenSanctions | PEP, Sanctions & Adverse Media Data | API Subscription (Standard) | 0 | 200 | 0
On-Chain Forensics | Chainalysis / TRM Labs | Wallet Screening & Risk Forensics | Fintech Tier API License | 1500 | 750 | 0
Travel Rule Network | Notabene / Sygna | IVMS101 Cross-VASP Messaging | Network SaaS Tier | 1000 | 400 | 0
Cloud Infrastructure | AWS / DigitalOcean | API Servers, Postgres DB, Workers | Cloud Compute & Bandwidth | 0 | 250 | 0
Security & Pentesting | Third-Party Auditor | Cybersecurity & Smart Contract Audit | Pre-Launch Security Audit | 3500 | 0 | 0
TOTAL PROGRAM BUDGET |  |  |  | 0 | 0 | 0

## 6. BoG Sandbox Filing Checklist
BANK OF GHANA VASP SANDBOX SUBMISSION CHECKLIST
Statutory Document Dossier Required for Sandbox Approval under Act 1154
Item ID | Application Artifact / Document | Act 1154 Section | Owner | Status | Content Summary & Readiness
DOC-01 | VASP Executive Brief & Business Model | Act 1154 §15, §44 | Partner 3 | READY | TrustRail 3-Unit compliance layer architecture & financial model
DOC-02 | Fit & Proper Questionnaires (Directors/Officers) | Act 1154 §24-25 | All Partners | IN PROGRESS | Background checks, resumes, police clearances for all 3 partners
DOC-03 | AML/CFT Compliance & Operational Manual | Act 1154 §33, Act 1044 | Partner 2 | READY | Full CDD, EDD, STR/CTR 24h reporting and watchlist escalation protocols
DOC-04 | Technical Architecture & Security Dossier | Act 1154 §16, §36 | Partner 1 | READY | API specifications, HSM/MPC custody design, Base L2 settlement, uptime SLAs
DOC-05 | Customer Asset Segregation & Solvency Policy | Act 1154 §32, §40 | Partner 3 / 1 | IN PROGRESS | Ring-fenced bank escrow structure + segregated on-chain custody ledgers
DOC-06 | Data Protection & Privacy Policy | Act 1154 §27, Act 843 | Partner 2 | READY | PII masking controls, encryption at rest/transit, DPC certificate filing
DOC-07 | Consumer Protection & Whistleblower Policy | Act 1154 §34 | Partner 2 | READY | Anonymous grievance channel and consumer dispute resolution procedures
DOC-08 | Disaster Recovery & Business Continuity Plan | Act 1154 §35 | Partner 1 | IN PROGRESS | Multi-region failover, key backup recovery, and transaction rollback rules
DOC-09 | Sandbox Testing Scope & Risk Mitigation Plan | Act 1154 §43-50 | Partner 3 / 2 | IN PROGRESS | Participant volume caps, 6-month trial metrics, and graduation criteria

## 7. Corporate & Reg Guide
GHANA CORPORATE & REGULATORY STEP-BY-STEP SETUP GUIDE
Detailed Blueprint for Company Formation, Statutory Tax/Pension, Data Protection & VASP Licensing
Step # | Government Body / Agency | Statutory Requirement | Procedure & Practical Guidance | Target Window
STEP 1: Incorporation | Office of Registrar of Companies (ORC) | Company Limited by Shares (Act 992) | File Form 3 with ORC. Object clauses MUST explicitly state 'Virtual Asset Infrastructure, Payment Systems, KYC/AML Compliance Services'. Minimum 3 directors (at least 1 independent, 1 resident in Ghana per Act 1154 §23). Qualified Company Secretary required. | Weeks 1 - 2
STEP 2: Tax & TIN | Ghana Revenue Authority (GRA) | Corporate TIN & Tax Registration | Register for corporate TIN upon incorporation. Setup GRA online portal for VAT, Withholding Tax (WHT) and corporate income tax. Obtain initial Tax Clearance Certificate (TCC). | Weeks 2 - 3
STEP 3: Pensions | Social Security & National Ins. (SSNIT) | SSNIT Employer Registration | Register company with SSNIT and obtain SSNIT Employer Number and Certificate. Mandatory document required for NIA direct API onboarding and BoG licensing. | Weeks 2 - 3
STEP 4: Physical Office | Local MMDA (e.g. AMA) | Registered Physical Office & Operating Permit | Secure physical commercial office address in Accra (mandatory under Act 1154 §21). Obtain Business Operating Permit (BOP) from Municipal/Metropolitan Assembly. | Weeks 2 - 4
STEP 5: Data Protection | Data Protection Commission (DPC) | Data Controller Certification (Act 843) | Register company as Data Controller & Data Processor with DPC. Appoint/certify Data Protection Officer (DPO). File privacy policies and biometric data impact assessment. | Weeks 3 - 6
STEP 6: AML & FIC Reg | Financial Intelligence Centre (FIC) | goAML Registration & MLRO Appointment | Formally notify FIC of designated Money Laundering Reporting Officer (MLRO). Create Organization Account on goAML portal (reporting.fic.gov.gh) for 24h STR filing. | Weeks 4 - 7
STEP 7: Banking & Float | Tier-1 Partner Bank (Stanbic/Ecobank) | Ring-Fenced Client Float Trust Account | Open operational bank accounts. Execute formal Escrow / Trust Agreement for ring-fenced customer cedi float (Act 1154 §32). Customer funds must never sit on balance sheet. | Weeks 5 - 9
STEP 8: NIA Enterprise | National Identification Authority (NIA) | NIR Direct Verification Access | Submit formal onboarding request to idverification@nia.gov.gh attaching Certificate of Incorporation, SSNIT, DPC certificate, and technical architecture dossier. | Weeks 8 - 11
STEP 9: BoG Sandbox | Bank of Ghana (VARO / VAD) | VASP Regulatory Sandbox Grant (Act 1154 §43-50) | Submit 9-part statutory application binder to VARO. Pay application fee. Conduct supervisory demonstration of TrustRail-KYC, TrustRail-AML, and CediRamp on Base. | Weeks 8 - 14
STEP 10: Full Licence | Bank of Ghana (VARO) | Full VASP Operating Licence (Act 1154 §14-20) | Complete 6-12 month sandbox testing cycle meeting volume and risk thresholds. Transition to full VASP Category 1, 3, and 4 Operating Licences. | Month 6 - 12